## Sheet1
No | Tasks | Status | Responsibility
1 | Electrical Drawing | - Completed drawing for A23, H2, KM26, Y1, H1, B3, KM25, KM16, KM17 but might need changes based on Mr Ivan input. - Incomplete drawing for SM5 because it uses 12VDC coil. - Will start for BRAVAN1, BRAVAN2, SU1 | Syafiq/ Ivan
2 | Panel Wiring | Done for all except SM5 | Maintenance
3 | Panel Installation to machines | Done for KM25 only | Maintenance
4 | Wiring from Panel to machines | Pending (Need to plan for machine stop) | Maintenance
5 | HMI Panel Installation | Pending | Maintenance
6 | PLC and HMI programming | Done | Syafiq
7 | Upload PLC and HMI program to machines | Pending | Syafiq
8 | Trunking for Ethernet and Power Supply to all Panel | Pending (Need to plan for machine stop/ Do during offday) | Contractor
9 | Website Integrations | Pending. Need to connect to the PLCs before can integrate | Syafiq